## Info
Integrated Project Management Sourcebook
A Technical Guide to Project Scheduling, Risk and Control
written by: | Mario Vanhoucke
Published by: | Springer
Website: | www.or-as.be/books
This book is intended to be the Integrated Project Management Sourcebook for students of any Project Management course focusing on the integration between baseline scheduling, schedule risk analysis and project control. This integration is known as "Dynamic Scheduling" or "Integrated Project Management and Control". The book is intended to be a technical guide that contains a set of +70 articles classified in the three main book themes, and each article contains links to other relevant articles of the book. The articles are accompanied with a set of questions to enable the reader to test his/her knowledge and understanding of the article’s theme, for which the answers are provided at the end of this book.
The book offers a valuable resource for anyone who wants to understand the technical details and underlying mechanisms of dynamic scheduling methods for projects. It is intended for students, professionals and academics with an interest and/or experience in the quantitative mechanisms used by the Baseline Scheduling, Schedule Risk Analysis and Earned Value & Earned Schedule Control concepts.
The content of this MS Excel solution file contains different tabs mentioned in the book
and summarised along the following lines:
Basline Scheduling
| BS9 | Solutions for "activity costs" questions
| BS11 | Solutions for "CPM" questions
| BS12 | Solutions for "slack definitions" questions
| BS13 | Solutions for "anomalies" questions
| BS15 | Solutions for "PERT" questions
| BS18 | Solutions for "priority rules" questions
| BS19 | Solutions for "generation schemes" questions
| BS20 | Solutions for "lower bounds" questions
| BS24 | Solutions for "project lead time" questions
| BS25 | Solutions for "net present value" questions
Risk Analysis
| RA4 | Solutions for "activity distributions" questions
| RA7 | Solutions for "criticality index" questions
| RA8 | Solutions for "Pearson’s cruciality index" questions
| RA9 | Solutions for "Kendall’s tau cruciality index" questions
| RA10 | Solutions for "Spearman’s cruciality index" questions
| RA11 | Solutions for "schedule sensitivity index" questions
| RA12 | Solutions for "significance index" questions
| RA15 | Solutions for "latest start schedules" questions
| RA17 | Solutions for "sizing buffers" questions
| RA18 | Solutions for "cut and paste method" questions
| RA19 | Solutions for "root squared error method" questions
| RA21 | Solutions for "adaptive resource tightness method" questions
Project Control
| PC14 | Solutions for "schedule adherence" questions
Symmaries
| Summary BS | Summary of all answers for all questions in the part "Baseline Scheduling" of the book
| Summary RA | Summary of all answers for all questions in the part "Schedule Risk Analysis" of the book
| Summary PC | Summary of all answers for all questions in the part "Project Control" of the book
E-mail: | mario.vanhoucke@ugent.be
Also read: | Taking Sound Business Decisions: From Rich Data to Better Solutions
The Art of Project Management: A Story about Work and Passion
Integrated Project Management and Control: First comes the theory, then the practice
Project Management with Dynamic Scheduling: Baseline scheduling, risk analysis and project control
Measuring Time: Improving project performance using Earned Value Management
Dynamic Scheduling on your Desktop

## BS9
Solution for question of the article BS9, Question 4
Correct solution
| Fixed Cost | Cost / Use | Cost / Unit (per month)
Administration cost | 5000 |  |  | 5000
Crane |  | 2000 |  | 4000 | You can assume that the crane won't be removed from the site when not used, so it must be paid
People (full-time) |  |  | 1750 | 6125 | Even though the FTE is not active at the end of month 4, he/she must be paid, but not for this project, so the cost should not be taken into account.
People (interim 1) |  |  | 2000 | 8000
People (interim 2) |  |  | 2000 | 7000 | The interim is not paid for the two weeks he/she doesn't work
30125
Alternative solution (in case of disagreement with previous solution)
| Fixed Cost | Cost / Use | Cost / Unit (per month)
Administration cost | 5000 |  |  | 5000
Crane |  | 2000 |  | 4000 | You can assume that the crane won't be removed from the site when not used, so it must be paid
People (full-time) |  |  | 1750 | 7000 | Even though the FTE is not active at the end of month 4, he/she must be paid, but not for this project. If the cost is still accounted on this project, you should pay this employee for 4 months.
People (interim 1) |  |  | 2000 | 8000
People (interim 2) |  |  | 2000 | 7000 | The interim is not paid for the two weeks he/she doesn't work
31000

## BS11
Solution for question of the article BS11, Questions 5 and 6
Network |  | Normal |  | Crash
Crashing cost per week
Activity | Successors | Time | Cost | Time | Cost
A | B, C, D | 3 | 6000 | 2 | 8000 | 2000
B | F | 5 | 12000 | 4 | 13500 | 1500
C | E | 5 | 16000 | 3 | 22000 | 3000
D | E | 4 | 8000 | 2 | 10000 | 1000
E | F | 2 | 6000 | 1 | 7500 | 1500
F | - | 3 | 14000 | 1 | 20000 | 3000
(x, y ) = (Normal duration, Crash duration)
The critical path with normal data |  |  | A - C - E - F | 13
The critical path with crash data |  |  | A - B - F | 7
or
|  |  | A - C - E - F | 7
The minimum cost (CP = 13) |  |  | 62000 | This is simply the sum of all costs for normal data
The minimum cost (CP = 7) |  |  | 81000 | This is simply the sum of all costs for crash data
But when you look carefully, activity D can be put at duration = 3 instead of its crash duration of 2, saving 1,000 euro.
|  |  | 80000 | This is the minimum cost for a critical path length CP = 7.

## BS12
Solution for question of the article BS12, Questions 3 to 7
|  | Buffer = 0 |  |  |  | Total | Safety | Free
| Duration | ES | LS | EF | LF | Slack | Slack | Slack
1 | 3 | 0 | 0 | 3 | 3 | 0 | n.a. | 0
2 | 2 | 3 | 5 | 5 | 7 | 2 | 2 | 2
3 | 4 | 3 | 3 | 7 | 7 | 0 | 0 | 0
4 | 3 | 7 | 7 | 10 | 10 | 0 | 0 | 0
5 | 1 | 7 | 11 | 8 | 12 | 4 | 4 | 4
6 | 2 | 10 | 10 | 12 | 12 | 0 | 0 | 0
7 | 5 | 12 | 12 | 17 | 17 | 0 | 0 | n.a.
|  | Buffer = 3 |  |  |  | Total | Safety | Free
| Duration | ES | LS | EF | LF | Slack | Slack | Slack
1 | 3 | 0 | 3 | 3 | 6 | 3 | n.a. | 0
2 | 2 | 3 | 8 | 5 | 10 | 5 | 2 | 2
3 | 4 | 3 | 6 | 7 | 10 | 3 | 0 | 0
4 | 3 | 7 | 10 | 10 | 13 | 3 | 0 | 0
5 | 1 | 7 | 14 | 8 | 15 | 7 | 4 | 4
6 | 2 | 10 | 13 | 12 | 15 | 3 | 0 | 0
7 | 5 | 12 | 15 | 17 | 20 | 3 | 0 | n.a.
The picture below shows on a simple example that the statement of question 7 is false for activity 1.
This is also the case for activity 2.

## BS13
Solution for question of the article BS13, Questions 3 and 4
Activity | Duration | Earliest Start | Earliest Finish
1 | 3 | 0 | 3
2 | 2 | 2 | 4
3 | 4 | 5 | 9
4 | 3 | 6 | 9
5 | 1 | 8 | 9
6 | 2 | 7 | 9
|  | Project duration | 9
Change the durations (decrease by -1) and only for activity 4 the project duration will increase!

## BS15
Solution for question of the article BS15, Questions 3 to 6
Activity | Duration |  |  | Expected | Standard
| a | m | b | Duration | Deviation
1 | 1 | 4 | 7 | 4 | 1
2 | 4 | 5 | 7 | 5.1667 | 0.5
3 | 1.5 | 2.5 | 3 | 2.4167 | 0.25
4 | 1 | 6 | 13 | 6.3333 | 2
5 | 0.5 | 2 | 8.5 | 2.8333 | 1.3333
6 | 1 | 4 | 4 | 3.5 | 0.5
|  |  | Critical path | 1 - 2 - 4 - 6
|  |  | Length CP | 19
|  |  | StDev CP | 2.3452
z-value for duration = 21
|  |  | z-value | 0.8528
|  |  | normdist (A) | 0.80312
|  |  | normdist (B) | 0.80312
90% percentile
|  |  | norminv | 22.0055

## BS18
Solution for question of the article BS18, Questions 5 and 6
Activity | Duration | Earliest Start | Earliest Finish | Resource Use | Work Content | Cumulative Work Content
S | 0 | 0 | 0 | 0 | - | -
1 | 1 | 0 | 1 | 3 | 3 | 6
2 | 2 | 0 | 2 | 2 | 4 | 13
3 | 3 | 1 | 4 | 1 | 3 | 15
4 | 3 | 2 | 5 | 3 | 9 | 12
5 | 3 | 4 | 7 | 3 | 9 | 9
6 | 3 | 5 | 8 | 1 | 3 | 3
E | 0 | 8 | 8 | 0 | - | -
Earliest finish time rule
1, 2, 3, 4, 5, 6
Greatest Cumulative Work Content
3, 2, 4, 5, 1, 6
In this list, some activities are put earlier than their predecessors (e.g. 3 comes before 1) but a schedule generation scheme will never schedule an activity earlier than its predecessor.
Therefore, it's much better to construct the list by taking both the precedence relations and the greatest cumulative work content into account, resuling in the following list below:
2, 4, 1, 3, 5, 6

## BS19
Solution for question of the article BS19, Questions 3, 5 and 6
Question 3
One could generate all possible lists and try to schedule them. The lists are [1, 2, 3, 4, 5], [1, 2, 3, 5, 4], … but it's not really necessary.
Just try the earliest start schedule list [1, 4, 2, 5, 3] using the serial schedule generation scheme, and you will find the schedule shown below with a minimum duration of 5 time units.
Legend of picture:
x-axis: time
y-axis: resource use
However, whatever list you use with the parallel schedule generation scheme, the best possible schedule that can be found has a minimum duration of 6 (instead of the best possible 5) as shown below.
This is because the parallel SGS has a time-incrementation, starting at t = 0, activities 1 and 4 will always be scheduled (eligible activities). At the next time point t=1, no activities can be scheduled.
The next time point t=3, two eligible activities (2 and 5) are available. Whatever you choose, 2 or 5, the next activities will be scheduled in such a way that it results in a schedule of 6 time units.
Independently of what priority list you use, the parallel SGS will never find the optimal solution since activities 1 and 4 will always be scheduled at t=0.
I would be better to leave one unit of the resource idle, as is the case for the serial SGS (see schedule above) and start another activity at time 1 instead of 0, but this will never occur with a parallel SGS.
Legend of picture:
x-axis: time
y-axis: resource use
Questions 5 and 6 (other network!)
Priority list = [1, 3, 2, 5, 4, 6]
Serial Schedule Generation Scheme:
5 | 2
4
3 | 1 |  |  |  | 5 |  |  | 4
2
1 |  | 3 | [8 empty] | 6
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Activity Colour
1
2
3
4
5
6
Swapping 4 and 5 in the list would lead to the following list and schedule:
Priority list = [1, 3, 2, 4, 5, 6]
Serial Schedule Generation Scheme:
5 | 2
4 |  |  | 4 |  |  | 6
3 | 1 |  |  |  |  | 5
2
1 |  | 3
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Legend of picture:
x-axis: time
y-axis: resource use
These schedules can also be displayed as Gantt charts below.
In these charts, the y-axis now represents the activities, and obviously, the resource use is not displayed.
1
2
3
4
5
6
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
and
1
2
3
4
5
6
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13

## BS20
Solution for question of the article BS20, Question 7
Activity | Predecessors | Duration | Resource Use | Work Content
1 | - | 0 | 0 | 0
2 | 1 | 6 | 7 | 42
3 | 1 | 5 | 1 | 5
4 | 1 | 3 | 5 | 15
5 | 3 | 1 | 6 | 6
6 | 3 | 3 | 1 | 3
7 | 3 | 2 | 2 | 4
8 | 4 | 1 | 2 | 2
9 | 2 | 4 | 8 | 32
10 | 5 | 3 | 6 | 18
11 | 7 | 1 | 2 | 2
12 | 6, 10, 11 | 3 | 6 | 18
13 | 8, 12 | 5 | 8 | 40
14 | 9, 13 | 0 | 0 | 0
187
Critical path based lower bound |  | 17
The critical path based lower bound is equal to 17 units resulting from the path “1 - 3 - 5 - 10 - 12 - 13 - 14”.
Resource based lower bound |  | 19
The resource based lower bound for the example project can be calculated as follows:
Step 1. The total resource work content is equal to 6∗7+5∗1+3∗5+1∗6+3∗1+2∗ 2+1∗2+4∗8+3∗6+1∗2+3∗6+5∗8 = 187 (see column work content).
Step 2. Division of this total work content by the resource availability (10) is equal to 18.7, and after a roundup, it's equal to 19.
Critical sequence lower bound |  | 21
Step 1. The critical path is equal to 17 with activities "1 - 3 - 5 - 10 - 12 - 14".
Step 2. For each noncritical activity, the calculations are made as shown in the table below.
Step 3. The maximum value for Delta_e_i is equal to 4, which means that the CP of 17 will be increased by 4, resulting in a value of 21.
Activity | Duration | Earliest Start | Latest Finish | e_i | Delta_e_i
2 | 6 | 0 | 13 | 5 | 1
4 | 3 | 0 | 11 | 3 | 0
6 | 3 | 5 | 9 | 3 | 0
7 | 2 | 5 | 8 | 2 | 0
8 | 1 | 3 | 12 | 1 | 0
9 | 4 | 6 | 17 | 0 | 4
11 | 1 | 7 | 9 | 1 | 0
Note. For more information and detailed calculations, read the book "Project Management with Dynamic Scheduling: Baseline Scheduling, Risk Analysis and Project Control".

## BS24
Solution for question of the article BS24, Question 6
The Gantt charts below show the schedule with (critical chain) and without (critical path) taking the resource constraint of 8 units into account.
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Critical Path
1
2 | 2 | 2
3 | 4 | 4 | 4 | 4
4 | 3 | 3 | 3 | 3 | 3 | 3 | 3
5 |  |  | 4 | 4 | 4
6 |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2
7 | [7 empty] | 3 | 3 | 3 | 3
8 | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
9 | [11 empty] | 4 | 4
10
Total Resource Use: | 9 | 9 | 11 | 11 | 9 | 8 | 8 | 8 | 8 | 8 | 6 | 7 | 7
Critical Chain
1
2 | 2 | 2
3 | 4 | 4 | 4 | 4
4 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3
5 |  |  |  |  | 4 | 4 | 4
6 | [7 empty] | 2 | 2 | 2 | 2 | 2 | 2
7 | [9 empty] | 3 | 3 | 3 | 3
8 | [7 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
9 | [13 empty] | 4 | 4
10
Total Resource Use: | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7

## BS25
Solution for question of the article BS25, Questions 4 and 5
|  |  |  | Finish Times |  | Finish Times |  | Finish Times |  | Finish Times
Activity | Cash flow | Finish Times | npv | Q5 (a) | npv | Q5 (b) | npv | Q5 (c) | npv | Q5 (d) | npv
1 | -10 | 2 | -9.0484 | 9 | -6.3763 | 2 | -9.0484 | 9 | -6.3763 | 2 | -9.0484
2 | -30 | 9 | -19.1288 | 7 | -21.1406 | 9 | -19.1288 | 7 | -21.1406 | 9 | -19.1288
3 | 100 | 5 | 77.8801 | 12 | 54.8812 | 12 | 54.8812 | 12 | 54.8812 | 5 | 77.8801
4 | 50 | 13 | 26.1023 | 13 | 26.1023 | 13 | 26.1023 | 11 | 28.8475 | 13 | 26.1023
5 | -20 | 17 | -8.5483 | 17 | -8.5483 | 17 | -8.5483 | 16 | -8.9866 | 18 | -8.1314
6 | 35 | 18 | 14.2299 | 18 | 14.2299 | 18 | 14.2299 | 17 | 14.9595 | 14 | 17.3805
| alpha | 0.05 | 81.4868 |  | 59.1482 |  | 58.4879 |  | 62.1847 |  | 85.0542
[5 empty] | This npv is lower! |  | This npv is lower! |  | This npv is lower! |  | This npv is higher!

## RA4
Solution for question of the article RA04, Question 2
Parameters of a triangular distribution |  | Right skewed | Symmetry | Left skewed
lowest value: | a | 2 | 4 | 6 | 1 | 1 | 0
mode: | m | 5 | 6 | 7 | 3 | 3 | 3
highest value: | b | 6 | 8 | 10 | 5 | 6 | 5
Average | (a + m + b) / 3 | 4.3333 | 6 | 7.6667
Variance | (a^2 + m^2 + b^2 - am - ab - mb)/18 | 0.72222 | 0.66667 | 0.72222
See e.g. https://en.wikipedia.org/wiki/Triangular_distribution

## RA7
Solution for question of the article RA7, Questions 3 and 4
| Run 1 | Run 2 | Run 3 | Run 4
Duration Activity A | 8 | 10 | 12 | 10
Duration Activity B | 6 | 12 | 12 | 8
Duration of Project | 8 | 12 | 12 | 10
CI
Activity A Critical? | Yes | No | Yes | Yes | 0.75
Activity B Critical? | No | Yes | Yes | No | 0.5

## RA8
Solution for question of the article RA8, Questions 3 to 7
Questions 3 and 4
| Run 1 | Run 2 | Run 3 | Run 4 |  | CRI( r)
Duration Activity A | 8 | 10 | 12 | 10 |  | 0.8528
Duration Activity B | 6 | 12 | 12 | 8 |  | 0.98644
Duration of Project | 8 | 12 | 12 | 10
The calculations below are similar to the calculations above. Only the input values for durations have been changed.
Questions 5 and 6
| Run 1 | Run 2 | Run 3 | Run 4 | … | CRI( r)
Duration Activity A | 10 | 100 | 10 | 100 | … | 1
Duration Activity B | 20 | 20 | 20 | 20 | … | #DIV/0! | Deterministic value, so no correlation possible since standard deviation is equal to 0.
Duration of Project | 20 | 100 | 20 | 100 | …
Question 7
| Run 1 | Run 2 | Run 3 | Run 4 | … | CRI( r)
Duration Activity A | 10 | 100 | 10 | 100 | … | 0.57735
Duration Activity B | 10 | 10 | 100 | 100 | … | 0.57735
Duration of Project | 10 | 100 | 100 | 100 | …

## RA9
Solution for question of the article RA9, Questions 3 to 6
Questions 3 and 4
| Run 1 | Run 2 | Run 3 | Run 4
Duration Activity A | 8 | 10 | 12 | 10
Duration Activity B | 6 | 12 | 12 | 8
Duration of Project | 8 | 12 | 12 | 10
Kendall's Tau Rank | Act A | Act B |  | nrs = | 4
Run 1 & 2 | 1 | 1
Run 1 & 3 | 1 | 1
Run 1 & 4 | 1 | 1
Run 2 & 3 | 0 | 0
Run 2 & 4 | 0 | 1
Run 3 & 4 | 1 | 1
sum | 4 | 5
CRI(tau) | 0.33333 | 0.66667
The calculations below are similar to the calculations above. Only the input values for durations have been changed.
Question 5
| Run 1 | Run 2 | Run 3 | Run 4 | …
Duration Activity A | 10 | 100 | 10 | 100 | …
Duration Activity B | 20 | 20 | 20 | 20 | …
Duration of Project | 20 | 100 | 20 | 100 | …
Kendall's Tau Rank | Act A | Act B |  | nrs = | 4
Run 1 & 2 | 1 | 0
Run 1 & 3 | 0 | 0
Run 1 & 4 | 1 | 0
Run 2 & 3 | 1 | 0
Run 2 & 4 | 0 | 0
Run 3 & 4 | 1 | 0
sum | 4 | 0
CRI(tau) | 0.33333 | -1
Question 6
| Run 1 | Run 2 | Run 3 | Run 4 | …
Duration Activity A | 10 | 100 | 10 | 100 | …
Duration Activity B | 20 | 20 | 20 | 20 | …
Duration of Project | 30 | 120 | 30 | 120 | … | This row has also changed: Use SUM (serial) instead of MAX (parallel)
Kendall's Tau Rank | Act A | Act B |  | nrs = | 4
Run 1 & 2 | 1 | 0
Run 1 & 3 | 0 | 0
Run 1 & 4 | 1 | 0
Run 2 & 3 | 1 | 0
Run 2 & 4 | 0 | 0
Run 3 & 4 | 1 | 0
sum | 4 | 0
CRI(tau) | 0.33333 | -1

## RA10
Solution for question of the article RA10, Questions 3 to 7
Questions 3 and 4
| Run 1 | Run 2 | Run 3 | Run 4
Duration Activity A | 8 | 10 | 12 | 10
Duration Activity B | 6 | 12 | 12 | 8
Duration of Project | 8 | 12 | 12 | 10
Cruciality Index (rho)
Ranking Value A | 1 | 2.5 | 4 | 2.5 |  | (Note that the countif function is used to break ties (average values) in the RANK function)
Ranking Value B | 1 | 3.5 | 3.5 | 2
Ranking Value PD | 1 | 3.5 | 3.5 | 2
SUM
DiffRank ^2 (A vs PD) | 0 | 1 | 0.25 | 0.25 | 1.5
DiffRank ^2 (B vs PD) | 0 | 0 | 0 | 0 | 0
[5 empty] | nrs = | 4
CRI (rho) | 0.85 | 1
Questions 5
| Run 1 | Run 2 | Run 3 | Run 4 | …
Duration Activity A | 10 | 100 | 10 | 100 | …
Duration Activity B | 20 | 20 | 20 | 20 | …
Duration of Project | 20 | 100 | 20 | 100 | …
Cruciality Index (rho)
Ranking Value A | 1.5 | 3.5 | 1.5 | 3.5
Ranking Value B | 2.5 | 2.5 | 2.5 | 2.5
Ranking Value PD | 1.5 | 3.5 | 1.5 | 3.5
SUM
DiffRank ^2 (A vs PD) | 0 | 0 | 0 | 0 | 0
DiffRank ^2 (B vs PD) | 1 | 1 | 1 | 1 | 4
[5 empty] | nrs = | 4
CRI (rho) | 1 | 0.6
The calculations below are similar to the calculations above. Only the input values for durations have been changed.
Questions 6
| Run 1 | Run 2 | Run 3 | Run 4 | …
Duration Activity A | 10 | 100 | 10 | 100 | …
Duration Activity B | 10 | 10 | 100 | 100 | …
Duration of Project | 10 | 100 | 100 | 100 | …
Cruciality Index (rho)
Ranking Value A | 1.5 | 3.5 | 1.5 | 3.5
Ranking Value B | 1.5 | 1.5 | 3.5 | 3.5
Ranking Value PD | 1 | 3 | 3 | 3
SUM
DiffRank ^2 (A vs PD) | 0.25 | 0.25 | 2.25 | 0.25 | 3
DiffRank ^2 (B vs PD) | 0.25 | 2.25 | 0.25 | 0.25 | 3
[5 empty] | nrs = | 4
CRI (rho) | 0.7 | 0.7
Questions 7
| Run 1 | Run 2 | Run 3 | Run 4 | …
Duration Activity A | 10 | 100 | 10 | 100 | …
Duration Activity B | 10 | 10 | 100 | 100 | …
Duration of Project | 20 | 110 | 110 | 200 | … | This row has also changed: Use SUM (serial) instead of MAX (parallel)
Cruciality Index (rho)
Ranking Value A | 1.5 | 3.5 | 1.5 | 3.5
Ranking Value B | 1.5 | 1.5 | 3.5 | 3.5
Ranking Value PD | 1 | 2.5 | 2.5 | 4
SUM
DiffRank ^2 (A vs PD) | 0.25 | 1 | 1 | 0.25 | 2.5
DiffRank ^2 (B vs PD) | 0.25 | 1 | 1 | 0.25 | 2.5
[5 empty] | nrs = | 4
CRI (rho) | 0.75 | 0.75

## RA11
Solution for question of the article RA11, Questions 3 to 7
Questions 3 and 4
| Run 1 | Run 2 | Run 3 | Run 4
Duration Activity A | 8 | 10 | 12 | 10
Duration Activity B | 6 | 12 | 12 | 8
Duration of Project | 8 | 12 | 12 | 10
Activity A Critical? | Yes | No | Yes | Yes
Activity B Critical? | No | Yes | Yes | No
CI Act A | 0.75
CI Act B | 0.5
Sigma_SAD Act A | 1.633 | 1.4142
Sigma_SAD Act B | 3 | 2.5981
Sigma_SPD | 1.9149 | 1.9149
SSI Act A | 0.6396 | 0.55391
SSI Act B | 0.78335 | 0.6784
| StDev | StDev.P
Use the sample standard deviation (column B) instead of the population standard deviation (column C).
The calculations below are similar to the calculations above. Only the input values for durations have been changed.
Question 5
| Run 1 | Run 2 | Run 3 | Run 4 | …
Duration Activity A | 10 | 100 | 10 | 100 | …
Duration Activity B | 20 | 20 | 20 | 20 | …
Duration of Project | 20 | 100 | 20 | 100 | …
Activity A Critical? | No | Yes | No | Yes
Activity B Critical? | Yes | No | Yes | No
CI Act A | 0.5
CI Act B | 0.5
Sigma_SAD Act A | 51.9615
Sigma_SAD Act B | 0
Sigma_SPD | 46.188
SSI Act A | 0.5625
SSI Act B | 0
Questions 6 and 7
| Run 1 | Run 2 | Run 3 | Run 4 | …
Duration Activity A | 10 | 100 | 10 | 100 | …
Duration Activity B | 20 | 20 | 20 | 20 | …
Duration of Project | 30 | 120 | 30 | 120 | … | This row has also changed: Use SUM (serial) instead of MAX (parallel)
Activity A Critical? | Yes | Yes | Yes | Yes |  | This row has also changes: Activities are always critical in a serial network
Activity B Critical? | Yes | Yes | Yes | Yes |  | This row has also changes: Activities are always critical in a serial network
CI Act A | 1
CI Act B | 1
Sigma_SAD Act A | 51.9615
Sigma_SAD Act B | 0
Sigma_SPD | 51.9615
SSI Act A | 1
SSI Act B | 0

## RA12
Solution for question of the article RA12, Questions 3 to 6
Questions 3 and 4
| Run 1 | Run 2 | Run 3 | Run 4 | Expected Value
Duration Activity A | 8 | 10 | 12 | 10
Duration Activity B | 6 | 12 | 12 | 8
Duration of Project | 8 | 12 | 12 | 10 | 2.625
Activity A |  |  |  |  | SI
SSL | 0 | 2 | 0 | 0
SAD/(SAD+SSL) | 1 | 0.83333 | 1 | 1
SAD/(SAD+SSL)*SPD/E(SPD) | 3.0476 | 3.8095 | 4.5714 | 3.8095 | 0.95238
Activity B
SSL | 2 | 0 | 0 | 2
SAD/(SAD+SSL) | 0.75 | 1 | 1 | 0.8
SAD/(SAD+SSL)*SPD/E(SPD) | 2.2857 | 4.5714 | 4.5714 | 3.0476 | 0.90476
The calculations below are similar to the calculations above. Only the input values for durations have been changed.
Question 5
| Run 1 | Run 2 | Run 3 | Run 4 | Expected Value
Duration Activity A | 10 | 100 | 10 | 100
Duration Activity B | 20 | 20 | 20 | 20
Duration of Project | 20 | 100 | 20 | 100 | 15
Activity A |  |  |  |  | SI
SSL | 10 | 0 | 10 | 0
SAD/(SAD+SSL) | 0.5 | 1 | 0.5 | 1
SAD/(SAD+SSL)*SPD/E(SPD) | 0.66667 | 6.6667 | 0.66667 | 6.6667 | 0.91667
Activity B
SSL | 0 | 80 | 0 | 80
SAD/(SAD+SSL) | 1 | 0.2 | 1 | 0.2
SAD/(SAD+SSL)*SPD/E(SPD) | 1.3333 | 1.3333 | 1.3333 | 1.3333 | 0.33333
Question 6
| Run 1 | Run 2 | Run 3 | Run 4 | Expected Value
Duration Activity A | 10 | 100 | 10 | 100
Duration Activity B | 20 | 20 | 20 | 20
Duration of Project | 30 | 120 | 30 | 120 | 18.75 | This row has also changed: Use SUM (serial) instead of MAX (parallel)
Activity A |  |  |  |  | SI
SSL | 0 | 0 | 0 | 0 |  | This row has also changed: the SSL = 0 for every activity in a serial network
SAD/(SAD+SSL) | 1 | 1 | 1 | 1
SAD/(SAD+SSL)*SPD/E(SPD) | 1.6 | 6.4 | 1.6 | 6.4 | 1
Activity B
SSL | 0 | 0 | 0 | 0 |  | This row has also changed: the SSL = 0 for every activity in a serial network
SAD/(SAD+SSL) | 1 | 1 | 1 | 1
SAD/(SAD+SSL)*SPD/E(SPD) | 1.6 | 6.4 | 1.6 | 6.4 | 1

## RA15
Solution for question of the article RA15, Questions 3 to 5
Below you find the critical path (ASAP and ALAP) and two options for the critical chain. Copy paste them in the schedule to the left to see possible resource conflicts.
Question 3
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | Critical Path (ASAP)
1 | 1 | 1 | [22 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
2 |  |  | 1 | [20 empty] | 1 | bar: 1 to 2
3 |  |  |  | 1 | 1 | 1 | 1 | [16 empty] | 2 | bar: 3
4 | [7 empty] | 1 | 1 | [14 empty] | 3 | bar: 3 to 6
5 | [9 empty] | 1 | 1 | 1 | 1 | [10 empty] | 4 | bar: 4 to 5
5 | bar: 7 to 10
Question 4 | bar: 1
Critical Path (ALAP)
Resource A | [23 empty] | 1 | bar: 1 to 2
1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | bar: 4
2 | [23 empty] | 3 | bar: 3 to 6
3 | [23 empty] | 4 | bar: 5 to 6
4 | [23 empty] | 5 | bar: 7 to 10
5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Question 5 | bar: 1
Total | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Critical Chain (option 1)
1 | bar: 1 to 2
Resource B | [23 empty] | 2 | bar: 3
1 | [23 empty] | 3 | bar: 4 to 7
2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | bar: 8 to 9
3 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | bar: 10 to 13
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Question 5 | bar: 1
5 | [23 empty] | Critical Chain (option 2)
Total | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | bar: 1 to 2
2 | bar: 3
3 | bar: 6 to 9
4 | bar: 4 to 5
5 | bar: 10 to 13

## RA17
Solution for question of the article RA17, Questions 2 to 5
| Safe | Aggressive | Delta | Standard |  | RA17. Calculating variances and standard deviations
Activity | Duration | Duration | Duration | Deviation | Successors |  | Q2. | Critical Chain = Critical Path = 1 - 3 - 5 - 6 - 7 based on the aggressive time durations (total duration = 16 time units)
1 | 6 | 4 | 2 | 1 | 2, 3 |  | Q3. | Variance of CC = 1^2 + 2^2 + 0.5^2 + 0.5^2 + 1^2 = 6.5
2 | 5 | 3 | 2 | 1 | 4 |  | Q4. | Variance of FC (2 - 4) = 1^2 + 1^2 = 2
3 | 10 | 6 | 4 | 2 | 5 |  | Q5. | 1.4142
4 | 5 | 3 | 2 | 1 | 6
5 | 2 | 1 | 1 | 0.5 | 6
6 | 2 | 1 | 1 | 0.5 | 7
7 | 6 | 4 | 2 | 1 | -

## RA18
Solution for question of the article RA18, Questions 1 to 5
Results from RA17:
| Safe | Aggressive | Delta | Standard |  |  | Critical Chain = Critical Path = 1 - 3 - 5 - 6 - 7 based on the aggressive time durations (total duration = 16 time units)
Activity | Duration | Duration | Duration | Deviation | Successors |  | Critical Chain = Critical Path = 1 - 3 - 5 - 6 - 7 based on the aggressive time durations (total duration = 16 time units)
1 | 6 | 4 | 2 | 1 | 2, 3 |  | Variance of CC = 1^2 + 2^2 + 0.5^2 + 0.5^2 + 1^2 = 6.5
2 | 5 | 3 | 2 | 1 | 4 |  | Variance of FC (2 - 4) = 1^2 + 1^2 = 2
3 | 10 | 6 | 4 | 2 | 5
4 | 5 | 3 | 2 | 1 | 6 | RA18. Cut and paste method
5 | 2 | 1 | 1 | 0.5 | 6 |  | Q1. | Length = 50% of 16 = 8 time units
6 | 2 | 1 | 1 | 0.5 | 7 |  | Q2. | Length = 50% of 6 = 3 time units
7 | 6 | 4 | 2 | 1 | - |  | Q3. | The cut and paste method ignores the long tail and takes 50% of the short durations, so it will probably underestimate the real duration.
[7 empty] | Q4. | A high value for the coefficient of variation means that standard deviation is likely to be high compared to the average durations. The cut and paste method ignores the standard deviation.
[7 empty] | Q5. | This activity has no risk and should therefore not be taken into consideration when buffering the critical chain.

## RA19
Solution for question of the article RA19, Questions 1 to 4
Results from RA17:
| Safe | Aggressive | Delta | Standard |  |  | Critical Chain = Critical Path = 1 - 3 - 5 - 6 - 7 based on the aggressive time durations (total duration = 16 time units)
Activity | Duration | Duration | Duration | Deviation | Successors |  | Critical Chain = Critical Path = 1 - 3 - 5 - 6 - 7 based on the aggressive time durations (total duration = 16 time units)
1 | 6 | 4 | 2 | 2 | 2, 3
2 | 5 | 3 | 2 | 2 | 4 | RA19. Root squared error method
3 | 10 | 6 | 4 | 4 | 5 |  | The standard deviation of the project activities is assumed to be equal to the difference between aggressive and safe durations in the RSEM.
4 | 5 | 3 | 2 | 2 | 6 |  | Variance of CC = 2^2 + 4^2 + 1^2 + 1^2 + 2^2 = 26
5 | 2 | 1 | 1 | 1 | 6 |  | Variance of FC = 2^2 + 2^2 = 8
6 | 2 | 1 | 1 | 1 | 7 |  | Q1. | 5.099
7 | 6 | 4 | 2 | 2 | - |  | Q2. | 2.8284
[7 empty] | Q3. | Written in the text
[7 empty] | Q4. | If it is assumed that the length of the critical chain is equal to its expected duration,
then it can be found on the normal distribution that adding two times sigma to the average is equal to the 97.5^th percentile,
and the probability to exceed is then equal to 2.5%.

## RA21
Solution for question of the article RA21, Questions 1 to 5
Activity | Safe | Aggressive | Delta | Resource |  |  | Standard | Successors |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | Below you find the critical path (ASAP) and two options for the critical chain. Copy paste them in the schedule to the left to see possible resource conflicts.
| Duration | Duration | Duration | A | B | C | Deviation | [25 empty] | Critical Path
1 | 6 | 4 | 2 | 1 | 1 | 1 | 1 | 2, 3 | 1 | 1 | 1 | 1 | 1 | [20 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
2 | 5 | 3 | 2 | 1 | 1 | 1 | 1 | 4 | 2 |  |  |  |  | 1 | 1 | 1 | [16 empty] | 1 | bar: 1 to 4
3 | 10 | 6 | 4 | 0 | 1 | 1 | 2 | 5 | 3 | [7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 2 | bar: 5 to 7
4 | 5 | 3 | 2 | 0 | 0 | 1 | 1 | 6 | 4 | [7 empty] | 1 | 1 | 1 | [13 empty] | 3 | bar: 5 to 10
5 | 2 | 1 | 1 | 0 | 1 | 0 | 0.5 | 6 | 5 | [13 empty] | 1 | [9 empty] | 4 | bar: 8 to 10
6 | 2 | 1 | 1 | 0 | 1 | 0 | 0.5 | 7 | 6 | [14 empty] | 1 | [8 empty] | 5 | bar: 11
7 | 6 | 4 | 2 | 1 | 0 | 0 | 1 | - | 7 | [15 empty] | 1 | 1 | 1 | 1 |  |  |  |  | 6 | bar: 12
7 | bar: 13 to 16
Resource A
[9 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Solving resource conflict (2 -> 3)
[9 empty] | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | bar: 1 to 4
[9 empty] | 3 | [23 empty] | 2 | bar: 5 to 7
[9 empty] | 4 | [23 empty] | 3 | bar: 8 to 13
[9 empty] | 5 | [23 empty] | 4 | bar: 8 to 10
[9 empty] | 6 | [23 empty] | 5 | bar: 14
[9 empty] | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 6 | bar: 15
[9 empty] | Total | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 7 | bar: 16 to 19
[9 empty] | Resource B | [23 empty] | Solving resource conflict (3 -> 2) and newly occuring conflict (2 -> 5)
[9 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | bar: 1 to 4
[9 empty] | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | bar: 11 to 13
[9 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | bar: 5 to 10
|  | Aggressive durations are displayed above each node | [6 empty] | 4 | [23 empty] | 4 | bar: 14 to 16
|  | Resource use is displayed below each node | [6 empty] | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | bar: 14
[9 empty] | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | bar: 17
[9 empty] | 7 | [23 empty] | 7 | bar: 18 to 21
[9 empty] | Total | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Resource C | [23 empty] | Resource tightness (duration project = 19)
[9 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC | 1: 1 - 2 - 3 - 5 - 6 - 7; 6: FC; 7: 4
[9 empty] | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1: Res A; 2: 0.28947; 7: Res A; 8: 0
[9 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1: Res B; 2: 0.78947; 7: Res B; 8: 0
[9 empty] | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1: Res C; 2: 0.34211; 7: Res C; 8: 0.5
[9 empty] | 5 | [24 empty] | 1: MAX; 2: 0.78947; 7: MAX; 8: 0.5
6
[9 empty] | 7 | [24 empty] | 2: 4.9007; 8: 1.5
[9 empty] | Total | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[33 empty] | Variance CC: | 2: 7.5
Variance FC: | bar: 2
Aggressive durations are displayed above each node
Resource use is displayed below each node

## PC14
Solution for question of the article PC14, Questions 4 and 5
Question 4
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9
Baseline Schedule | [10 empty] | PVi,ES |  | ES @ W5 | 4.5
1 | 5 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | 10 |  | AT | 5
2 |  |  | 10 | 20 | 30 | 30 | 30 | 30 | 30 |  | 25
3 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 5
4 | W6: 20; W7: 20; W8: 20; W9: 20 |  | 0
5 | W6: 10; W7: 20; W8: 20; W9: 20 |  | 0
6 |  |  |  | 20 | 40 | 40 | 40 | 40 | 40 |  | 30
7 | W6: 5; W7: 5; W8: 5; W9: 5 |  | 0
8 | W8: 10; W9: 20 |  | 0
PV | 5 | 10 | 25 | 55 | 85 | 120 | 130 | 140 | 150 | SUM | 70
p-factor
Real schedule (W7) | [10 empty] | EVi,AT |  | numerator
1 | 3.33 | 6.66 | 10 | 10 | 10 | 10 | 10 |  |  |  | 10 |  | 10
2 | W4: 7.5; W5: 15; W6: 22.5; W7: 30 |  | 15 |  | 15
3 | W4: 5; W5: 5; W6: 5; W7: 5 |  | 5 |  | 5
4 | [10 empty] | 0 |  | 0 | bar: W8
5 | [10 empty] | 0 |  | 0 | bar: W8 to W9
6 | W5: 40; W6: 40; W7: 40 |  | 40 |  | 30
7 | W6: 5; W7: 5 |  | 0 |  | 0
8
EV | 3.33 | 6.66 | 10 | 22.5 | 70 | 82.5 | 90 |  |  |  |  | SUM | 60
ES @ W5 | W2: 4.5 |  |  | p-factor | 0.85714
PVi,ES
Question 5 | bar: W1 to W2
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9
Baseline Schedule | [10 empty] | PVi,ES |  | ES @ W7 | 5.14
1 | 5 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | 10 |  | AT | 7
2 |  |  | 10 | 20 | 30 | 30 | 30 | 30 | 30 |  | 30
3 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 5
4 | W6: 20; W7: 20; W8: 20; W9: 20 |  | 2.8
5 | W6: 10; W7: 20; W8: 20; W9: 20 |  | 1.4
6 |  |  |  | 20 | 40 | 40 | 40 | 40 | 40 |  | 40
7 | W6: 5; W7: 5; W8: 5; W9: 5 |  | 0.7
8 | W8: 10; W9: 20 |  | 0
PV | 5 | 10 | 25 | 55 | 85 | 120 | 130 | 140 | 150 | SUM | 89.9
p-factor
Real schedule (W7) | [10 empty] | EVi,AT |  | numerator
1 | 3.33 | 6.66 | 10 | 10 | 10 | 10 | 10 |  |  |  | 10 |  | 10
2 | W4: 7.5; W5: 15; W6: 22.5; W7: 30 |  | 30 |  | 30
3 | W4: 5; W5: 5; W6: 5; W7: 5 |  | 5 |  | 5
4 | W7: 5 |  | 5 |  | 2.8
5 | [10 empty] | 0 |  | 0 | bar: W8 to W9
6 | W5: 40; W6: 40; W7: 40 |  | 40 |  | 40
7 | [10 empty] | 0 |  | 0 | bar: W8
8
EV | 3.33 | 6.66 | 10 | 22.5 | 70 | 77.5 | 90 | 0 | 0 |  |  | SUM | 87.8
ES @ W5 | W2: 4.5 |  |  | p-factor | 0.97664

## Summary BS
| Baseline scheduling |  |  |  | Questions | Your answer
| Topic |  |  | Quiz? | Article ID | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7
1 | Dynamic scheduling | An introduction to baseline scheduling |  | No | BS1 | - | - | - | - | - | - | -
2 | Network analysis | Project networks: Nodes and arcs or arcs and nodes? |  | Yes | BS2 | b | a | a | c | b | b | -
3 |  | Activity links: How to add precedence relations between activities? |  | Yes | BS3 | b | b* | a | d | b* | b | b*
4 |  | Activity links: The equivalence of minimal and maximal time-lags |  | Yes | BS4 | b | a | b* | d | d | a, d | -
5 |  | Activity constraints: Limiting the degrees of freedom of project activities |  | Yes | BS5 | b | a | a | b | b | b | -
6 | Resource analysis | Resource types: Renewable and consumable resources |  | Yes | BS6 | a | a | b | b | d | - | -
7 |  | The critical path or the critical chain? The difference caused by resources |  | Yes | BS7 | b | a | a* | d* | a* | - | -
8 |  | Linking resources to activities: Resource availability and resource demand |  | Yes | BS8 | a | a | a | - | - | - | -
9 |  | The cost of a project activity: Calculating the activity and/or resource costs |  | Yes | BS9 | b | a | a | c* | c | - | -
10 | Scheduling techniques | Critical path scheduling | Scheduling projects: How to determine the critical path using activity slack calculations? | Yes | BS10 | a | b* | a | a | - | - | -
11 |  |  | The Critical Path Method (CPM): Incorporating activity time/cost trade-offs in a project schedule | Yes | BS11 | b | b* | a | a | a* | c* | -
12 |  |  | Activity slack: Total, safety and free slack definitions | Yes | BS12 | a | b | c* | c* | c* | c* | e*
13 |  |  | The critical path with non-zero time-lags: An anomaly or just a mistake? | Yes | BS13 | a | b | a* | d* | - | - | -
14 |  |  | The Project Scheduling Game (PSG): Time/cost trade-offs on a computer screen | Yes | BS14 | b | b* | a | a | - | - | -
15 |  |  | The Program Evaluation and Review Technique (PERT): Incorporating activity time variability in a project schedule | Yes | BS15 | b | c | a* | a* | c* | d* | -
16 |  |  | A critical note on PERT: A manual simulation study | Yes | BS16 | a | c | b | b* | - | - | -
17 |  | Resource scheduling | Optimizing regular scheduling objectives: Priority rule based scheduling | Yes | BS17 | b | a | a | b | b | - | -
18 |  |  | Optimizing regular scheduling objectives: Priority rule calculations | Yes | BS18 | b* | b | a* | a | c* | e* | -
19 |  |  | Optimizing regular scheduling objectives: Schedule generation schemes | Yes | BS19 | a | b | b* | a | c* | a* | -
20 |  |  | What is my scheduling objective? Lower bounds on the total project duration | Yes | BS20 | a | b | a | b* | a | b | f*
21 |  |  | Heuristic project scheduling: Validating the quality of a project schedule | Yes | BS21 | a* | b* | a | b | b* | b | -
22 |  | Scheduling objectives | Resource constrained project scheduling: What is my scheduling objective? | Yes | BS22 | a | b* | a | b | b, d | - | -
23 |  |  | Resource constrained project scheduling: Regular and non-regular scheduling objectives | Yes | BS23 | a | b | c | b* | c* | - | -
24 |  |  | What is my scheduling objective? Minimizing the project lead time | Yes | BS24 | b | a | b | a | b* | a* | -
25 |  |  | What is my scheduling objective? Maximizing the net present value | Yes | BS25 | b* | b* | a* | c* | d* | - | -
26 |  |  | What is my scheduling objective? Minimizing the resource idle time | Yes | BS26 | c | d | b | a | - | - | -
27 |  |  | What is my scheduling objective? Leveling the use of resources | Yes | BS27 | a | b* | a* | b* | - | - | -
[5 empty] | Total number of questions: | 137
[5 empty] | Total number of comments: | 50
Comments:
[5 empty] | BS3 | Q2 | The statement should be true for a Finish-Start (FS) but not for Start-Finish (SF).
[5 empty] | BS3 | Q5 | The start-start relationship enforces that the start of both activities can be separated by no more than 3 time periods.
[5 empty] | BS3 | Q7 | As long as activity A finishes before activity B, all precedence relations are satisfied, and hence, activity A can have multiple start times.
[5 empty] | BS4 | Q3 | The statement is not always true, and depends on the durations of the activities.
[5 empty] | BS7 | Q3 | The critical path consists of activities 4, 7 and 8.
[5 empty] | BS7 | Q4 | The critical path consists of activities 1, 2, 5, 8 and 10.
[5 empty] | BS7 | Q5 | Paths B and C include activity 9, which is not on the CC since it can be shifted backwards. Path D does not include activity 8 which cannot be moved without increasing the duration of the complete project.
[5 empty] | BS9 | Q4 | Answer C is the correct solution if it is assumed that a full-time worker is not paid by the project budget when he/she is not active. Otherwise, answer D is correct. See MS Excel solution file tab "BS9".
[5 empty] | BS10 | Q2 | The earliest start time of an activity is the maximum of the earliest finishing time of all its predecessors.
[5 empty] | BS11 | Q2 | Decreasing the duration of an activity inflates the associated cost (more manpower, more expensive equipment, etc.)
[5 empty] | BS11 | Q5 | The critical path with normal data is equal to A - C - E - F with length 13 and the critical path with crash data is equal to A - B - F or A - C - E - F with length 7. See MS Excel solution file, tab "BS11".
[5 empty] | BS11 | Q6 | The minimum cost (CP = 13) is equal to 62,000 which is is simply the sum of all costs for normal data. The minimum cost (CP = 7) is equal to 80,000 and NOT 81,000. 81,000 is simply the sum of all costs for crash data but when you look carefully, activity D can be put at duration = 3 instead of its crash duration of 2, saving 1,000 euro. See MS Excel solution file, tab "BS11".
[5 empty] | BS12 | Q3 | The critical path length is equal to 17 time units. The earliest start of activity 5 equals 7 and the latest start equals 11, which results in a slack value of 4. See MS Excel solution file tab "BS12".
[5 empty] | BS12 | Q4 | All the predecessors of activity 5 are on the critical path, hence the safety slack is equal to the total slack.
[5 empty] | BS12 | Q5 | See MS Excel solution file tab "BS12".
[5 empty] | BS12 | Q6 | The introduction of a buffer has no impact on the free slack of activity 2. See MS Excel solution file tab "BS12".
[5 empty] | BS12 | Q7 | See MS Excel solution file tab "BS12".
[5 empty] | BS13 | Q3 | The activity start times are equal to 0, 2, 5, 6, 8, 7 for activities 1 to 6, and the activity finish times are equal to 3, 4, 9, 9, 9, 9. See MS Excel solution file tab "BS13".
[5 empty] | BS13 | Q4 | See MS Excel solution file tab "BS13".
[5 empty] | BS14 | Q2 | The aim of the game is to cope with uncertainty in a reactive way.
[5 empty] | BS15 | Q3 | The critical path contains the activities 1, 2, 4 and 6.
[5 empty] | BS15 | Q4 | Calculate as the square root of the sum of the variances of the activities on the CP (1+0.25+4+0.25). See MS Excel solution file tab "BS15".
[5 empty] | BS15 | Q5 | Use the normal distribution calculations (21 - 19) / 2.35 to calculate the z-value and use MS Excel or normal tables to calculate the probability. See MS Excel solution file tab "BS15". (using excel NORMDIST function)
[5 empty] | BS15 | Q6 | Use the average and standard deviation values of previous questions and find the 90th percentile. See MS Excel solution file tab "BS15". (using excel NORMINV function)
[5 empty] | BS16 | Q4 | For independent paths, answer B is the correct one. For dependent paths it is not correct.
[5 empty] | BS18 | Q1 | The word "total" assumes that both direct (immediate) and indirect successors are taken into account, so the statement is false.
[5 empty] | BS18 | Q3 | Activity 5 is unrelated to activity 6.
[5 empty] | BS18 | Q5 | The earliest finish times are equal to 1, 2, 4, 5, 7 and 8 for activities 1 to 6. See MS Excel solution file tab "BS18".
[5 empty] | BS18 | Q6 | The cumulative resource work content is equal to 6, 13, 15, 12 9 and 3 for activities 1 to 6 so the list is normally equal to [3, 2, 4, 5, 1, 6]. However, some activities come earlier in the list than predecessor activities (e.g. 3 comes before 1) which will never be possible. Taking both the precedence relations and the cumulate resource work content into account will transform the list to list [2, 4, 1, 3, 5, 6]. See MS Excel solution file tab "BS18".
[5 empty] | BS19 | Q3 | This is an advanced questions, and the answer is illustrated in the MS Excel solution file, tab "BS19".
[5 empty] | BS19 | Q5 | The schedule has finish times equal to 1, 2, 4, 10, 7 and 13 for activities 1 to 6, respectively. See MS Excel solution file, tab "BS19".
[5 empty] | BS19 | Q6 | Since activity 4 can now be scheduled in parallel with activity 3, a reduction of at least 2 time periods will be obtained. Due to the reduction, activities 5 and 6 can solve be scheduled in parallel, resulting in a total reduction of 5 time units. See MS Excel solution file tab, "BS19".
[5 empty] | BS20 | Q4 | The actual duration will be larger than or equal to the lower bound.
[5 empty] | BS20 | Q7 | The CPLB = 17, the RBLB = 19 and the CSLB = 21. See MS Excel file, tab "BS20" or the book "Project Management with Dynamic Scheduling: Baseline Scheduling, Risk Analysis and Project Control" from which this example was taken.
[5 empty] | BS21 | Q1 | An upper bound for a maximization problem is identical to a lower bound for a minimization problem, and ignores some constraints (e.g. the resource constraints). It does not provide a feasible solution.
[5 empty] | BS21 | Q2 | A lower bound for a minimization problem ignores some constraints, but does not lead to a feasible solution. A heuristic search would provide an upper bound, and not a lower bound.
[5 empty] | BS21 | Q5 | A heuristic solution provides a lower bound for a maximization problem.
[5 empty] | BS22 | Q2 | This statement is false. While it is true for the minimization of the total project duration, it can be false for other scheduling objectives such as the net present value maximization.
[5 empty] | BS23 | Q4 | This statement is false. While it is true for the minimization of the total project duration, it can be false for other scheduling objectives such as the net present value maximization.
[5 empty] | BS23 | Q5 | One need more information on the schedule to determine which schedule is the best. The question does not follow the definition of regular measure of performance.
[5 empty] | BS24 | Q5 | Activities that are scheduled in parallel might still have a total resource use that is higher than the availability.
[5 empty] | BS24 | Q6 | The critical path is equal to activities 1, 2, 5, 8 and 10 with a duration of 13. Activities 2 and 4 cannot be scheduled in parallel and one of these activities must be delayed, leading to an increase in the total project duration of 2 time units. See MS Excel solution file tab "BS24". Note that there is also an alternative critical path equal to 1, 4, 7, 9, 10.
[5 empty] | BS25 | Q1 | The net present value should be higher than zero, not lower.
[5 empty] | BS25 | Q2 | These activities should be scheduled as late as possible.
[5 empty] | BS25 | Q3 | A lump sum payment is a huge positive cash flow, which should be scheduled as soon as possible.
[5 empty] | BS25 | Q4 | See MS Excel solution file tab "BS25".
[5 empty] | BS25 | Q5 | The new net present values are equal to € 59.15, € 58.49, € 62.18 and € 85.05 for options (a) to (d), respectively. See MS Excel solution file tab "BS25".
[5 empty] | BS27 | Q2 | While many project scheduling software tools often focus on the efficient use of resources (i.e. levelling), they mostly take the minimization of the total project duration as the main objective.
[5 empty] | BS27 | Q3 | This statement is true since the network is completely serial and hence both schedules will be identical.
[5 empty] | BS27 | Q4 | An earliest start schedule can have a very irregular resource use, despite the fact that no resource conflicts occur.

## Summary RA
| Risk analysis |  |  |  | Questions | Your answer
| Topic |  |  | Quiz? | Article ID | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8
1 | Dynamic scheduling | An introduction to risk management |  | No | RA1 | bar: Your answer Q1 to Your answer Q8
2 | Schedule risk analysis | Monte-Carlo simulations: How to imitate a project’s progress? |  | Yes | RA2 | b | c | b | b* | b | b* | c* | -
3 |  | Monte-Carlo simulations: Linking critical path schedules to project control |  | Yes | RA3 | b | d* | c | b | a* | a* | - | -
4 |  | Project risk: Statistical distributions or single point estimates? |  | Yes | RA4 | a | e* | b* | b* | - | - | - | -
5 |  | Schedule Risk Analysis: How to measure your baseline schedule’s sensitivity? |  | Yes | RA5 | b | d | c | c | a | b* | - | -
6 |  | Schedule Risk Analysis: Measuring the time sensitivity of an activity |  | Yes | RA6 | c | b | a* | c | b | b | - | -
7 |  | Time sensitivity measures | Measuring time sensitivity in a project: The criticality index | Yes | RA7 | b* | d | c* | a* | b* | f* | b | a*
8 |  |  | Measuring time sensitivity in a project: The cruciality index (Pearson’s product-moment) | Yes | RA8 | f* | f | b* | c* | e* | f* | d* | -
9 |  |  | Measuring time sensitivity in a project: The cruciality index (Kendall’s tau rank correlation) | Yes | RA9 | f | f | b* | c* | c* | b* | - | -
10 |  |  | Measuring time sensitivity in a project: The cruciality index (Spearman’s rank correlation) | Yes | RA10 | f | f | b* | d* | d* | e* | e* | -
11 |  |  | Measuring time sensitivity in a project: The schedule sensitivity index | Yes | RA11 | c* | e | b* | c* | d* | f* | a* | -
12 |  |  | Measuring time sensitivity in a project: The significance index | Yes | RA12 | b* | d | d* | c* | c* | e* | - | -
13 | Buffer management | Critical Chain/Buffer Management: Protecting the schedule against project delays |  | Yes | RA13 | b | a | b | b | a* | - | - | -
14 |  | Aggressive activity time estimates: Protecting against activity delays |  | Yes | RA14 | c | b | c | b | - | - | - | -
15 |  | Critical Chain/Buffer Management: (Dis-)advantages of scheduling projects as-late-as-possible |  | Yes | RA15 | d* | c | c* | d* | d* | b | - | -
16 |  | Critical Chain/Buffer Management: Adding buffers to a project schedule |  | Yes | RA16 | c* | b* | b* | d | b* | - | - | -
17 |  | Sizing CC/BM buffers | Critical Chain/Buffer Management: Sizing project and feeding buffers | Yes | RA17 | b | c* | e* | b* | b* | - | - | -
18 |  |  | Sizing CC/BM buffers: The cut and paste method | Yes | RA18 | a* | b* | c* | c* | a* | - | - | -
19 |  |  | Sizing CC/BM buffers: The root squared error method | Yes | RA19 | b* | c* | b* | c* | - | - | - | -
20 |  |  | Sizing CC/BM buffers: The adaptive procedure with density | Yes | RA20 | d* | c* | b* | d* | c* | e* | - | -
21 |  |  | Sizing CC/BM buffers: Adaptive procedure with resource tightness (APRT) | Yes | RA21 | d* | c* | a* | d* | c* | - | - | -
22 |  | Critical Chain/Buffer Management: Inserting buffers in a resource-constrained schedule |  | Yes | RA22 | a* | a | a | b* | - | - | - | -
23 |  | Inserting buffers in a schedule: The problem with resource conflicts |  | Yes | RA23 | a | a | a | a | b* | - | - | -
[5 empty] | Total number of questions: | Your answer Q1: 124
[5 empty] | Total number of comments: | Your answer Q1: 79
Comments:
[5 empty] | RA2 | Your answer Q1: Q4; Your answer Q2: During Monte Carlo simulations, the critical path might change for every simulation run.
[5 empty] | RA2 | Your answer Q1: Q6; Your answer Q2: When the logic of the random generator discussed in the article is followed, the generated number will be equal to 5 since 0.20 < 0.379403 < 0.7.
[5 empty] | RA2 | Your answer Q1: Q7; Your answer Q2: Each simulation runs generates numbers independent from the previous run.
[5 empty] | RA3 | Your answer Q1: Q2; Your answer Q2: The SPI(t) indicator should be compared against the value 1, and not zero.
[5 empty] | RA3 | Your answer Q1: Q5; Your answer Q2: The SPI(t) indicators reports a project delivery ahead of schedule, and the final result shows that RD < PD, illustrating a final early delivery.
[5 empty] | RA3 | Your answer Q1: Q6; Your answer Q2: The SPI(t) indicators reports a project delivery ahead of schedule, but the final result shows that RD > PD, illustrating a final late delivery. Exactly the opposite!
[5 empty] | RA4 | Your answer Q1: Q2; Your answer Q2: The standard deviation of a triangular distribution is equal to $\frac{a^2 + m^2 + b^2 - am - ab - mb}{18}$ so it can be easily seen using values for $a$, $b$ and $c$ that the variances for distributions 1 and 3 will be the same, and bigger than the variance for distribution 2. See MS Excel solution file, tab "RA4".
[5 empty] | RA4 | Your answer Q1: Q3; Your answer Q2: Using interval estimates will produce several critical paths, i.e. one for each simulation run. In doing so, sensitivity metrics can be produced that express the likelihood of being a critical path. Finding a new deterministic path is not the goal of simulation.
[5 empty] | RA4 | Your answer Q1: Q4; Your answer Q2: The PERT technique makes some assumptions that are not 100\% correct and therefore the results of PERT might slightly differ from simulated results, even when the same distributions are used. See e.g. article "BS16" for more information.
[5 empty] | RA5 | Your answer Q1: Q6; Your answer Q2: Such an activity has a high probability of being critical, but the impact of unexpected changes in the durations will not have a huge impact on the project duration, and hence, it does not deserve much attention.
[5 empty] | RA6 | Your answer Q1: Q3; Your answer Q2: Since the CRI is measured as an absolute value, both values close to 1 and -1 will results in values close to 1.
[5 empty] | RA7 | Your answer Q1: Q1; Your answer Q2: In a serial network, every activity lies on the critical path, regardless of its duration.
[5 empty] | RA7 | Your answer Q1: Q3; Your answer Q2: The number of runs that activity A is critical = 3 and total number of runs = 4 so CI = $\frac{3}{4} =0.75$. See MS Excel solution file, tab "RA7".
[5 empty] | RA7 | Your answer Q1: Q4; Your answer Q2: The number of runs that activity B is critical = 2 and total number of runs = 4 so CI = $\frac{2}{4} = 0.50$. See MS Excel solution file, tab "RA7".
[5 empty] | RA7 | Your answer Q1: Q5; Your answer Q2: When an activity is added to the network, the number of times the old activities A and B lie on the critical path can remain the same or reduce, but never increase.
[5 empty] | RA7 | Your answer Q1: Q6; Your answer Q2: The number of times that activity A will lie on the critical path will probably increase due to the longer path as a result of successor C. The number of times activity B lies on the critical path will decrease (or remain the same).
[5 empty] | RA7 | Your answer Q1: Q8; Your answer Q2: Activity A will be critical only when activity B has a duration of 10 (50%) and activity C has a duration of 10 (50%). The probability is equal to 50% * 50% = 25%.
[5 empty] | RA8 | Your answer Q1: Q1; Your answer Q2: Since the CRI is measured as a correlation, any value can be possible.
[5 empty] | RA8 | Your answer Q1: Q3; Your answer Q2: See MS Excel solution file, tab "RA8".
[5 empty] | RA8 | Your answer Q1: Q4; Your answer Q2: See MS Excel solution file, tab "RA8".
[5 empty] | RA8 | Your answer Q1: Q5; Your answer Q2: See MS Excel solution file, tab "RA8".
[5 empty] | RA8 | Your answer Q1: Q6; Your answer Q2: Since there is no variability in the duration, the correlation has no value. See MS Excel solution file, tab 'RA8".
[5 empty] | RA8 | Your answer Q1: Q7; Your answer Q2: See MS Excel solution file, tab "RA8".
[5 empty] | RA9 | Your answer Q1: Q3; Your answer Q2: See MS Excel solution file, tab "RA9".
[5 empty] | RA9 | Your answer Q1: Q4; Your answer Q2: See MS Excel solution file, tab "RA9".
[5 empty] | RA9 | Your answer Q1: Q5; Your answer Q2: See MS Excel solution file, tab "RA9".
[5 empty] | RA9 | Your answer Q1: Q6; Your answer Q2: See MS Excel solution file, tab "RA9".
[5 empty] | RA10 | Your answer Q1: Q3; Your answer Q2: See MS Excel solution file, tab "RA10".
[5 empty] | RA10 | Your answer Q1: Q4; Your answer Q2: See MS Excel solution file, tab "RA10".
[5 empty] | RA10 | Your answer Q1: Q5; Your answer Q2: See MS Excel solution file, tab "RA10".
[5 empty] | RA10 | Your answer Q1: Q6; Your answer Q2: See MS Excel solution file, tab "RA10".
[5 empty] | RA10 | Your answer Q1: Q7; Your answer Q2: See MS Excel solution file, tab "RA10".
[5 empty] | RA11 | Your answer Q1: Q1; Your answer Q2: In a serial network, the value for the CI is equal to 1 for all activities.
[5 empty] | RA11 | Your answer Q1: Q3; Your answer Q2: See MS Excel solution file, tab "RA11".
[5 empty] | RA11 | Your answer Q1: Q4; Your answer Q2: See MS Excel solution file, tab "RA11".
[5 empty] | RA11 | Your answer Q1: Q5; Your answer Q2: See MS Excel solution file, tab "RA11".
[5 empty] | RA11 | Your answer Q1: Q6; Your answer Q2: See MS Excel solution file, tab "RA11".
[5 empty] | RA11 | Your answer Q1: Q7; Your answer Q2: See MS Excel solution file, tab "RA11".
[5 empty] | RA12 | Your answer Q1: Q1; Your answer Q2: For a serial project, SSL = 0 for all activities. The formula for the SI can hence be written as follows: SI = $E \left \{ \frac{SAD}{SAD} * \frac{SPD}{E(SPD)} \right \} = E \left \{ \frac{SPD}{E(SPD)} \right \} = 1.0$
[5 empty] | RA12 | Your answer Q1: Q3; Your answer Q2: See MS Excel solution file, tab "RA12".
[5 empty] | RA12 | Your answer Q1: Q4; Your answer Q2: See MS Excel solution file, tab "RA12".
[5 empty] | RA12 | Your answer Q1: Q5; Your answer Q2: See MS Excel solution file, tab "RA12".
[5 empty] | RA12 | Your answer Q1: Q6; Your answer Q2: See MS Excel solution file, tab "RA12".
[5 empty] | RA13 | Your answer Q1: Q5; Your answer Q2: The CC/BM technique allows the use of buffers to monitor the performance of the project, rather than monitoring individual activities, and hence, it can be considered as a top-down approach, similar to Earned Value Management.
[5 empty] | RA15 | Your answer Q1: Q1; Your answer Q2: This is exactly the principle of the net present value, as discussed in article BS25.
[5 empty] | RA15 | Your answer Q1: Q3; Your answer Q2: See MS Excel solution file, tab "RA15".
[5 empty] | RA15 | Your answer Q1: Q4; Your answer Q2: See MS Excel solution file, tab "RA15".
[5 empty] | RA15 | Your answer Q1: Q5; Your answer Q2: See MS Excel solution file, tab "RA15".
[5 empty] | RA16 | Your answer Q1: Q1; Your answer Q2: There is no such concept as cost buffer in the CC/BM method.
[5 empty] | RA16 | Your answer Q1: Q2; Your answer Q2: Given that the aggressive time estimates are used it is normal that a substantial fraction of the buffer will be consumed, only when the buffer consumption is more than could reasonably be expected the project manager should take action.
[5 empty] | RA16 | Your answer Q1: Q3; Your answer Q2: Ideally, buffers should be sized according to the variability in the chain (answer b), but maybe the total duration of the chain could also be taken into account (so answer c should also be considered as correct).
[5 empty] | RA16 | Your answer Q1: Q5; Your answer Q2: Resource buffers are not time buffers, but only warning signals to assure the resource is ready when the activity starts.
[5 empty] | RA17 | Your answer Q1: Q2; Your answer Q2: Critical Chain = Critical Path = 1 - 3 - 5 - 6 - 7 based on the aggressive time durations (total duration = 16 time units). See MS Excel solution file, tab "RA17".
[5 empty] | RA17 | Your answer Q1: Q3; Your answer Q2: Variance of critical chain = $1^2 + 2^2 + 0.5^2 + 0.5^2 + 1^2 = 6.5$.
[5 empty] | RA17 | Your answer Q1: Q4; Your answer Q2: Variance of feeding chain (2 - 4) = 1^2 + 1^2 = 2.
[5 empty] | RA17 | Your answer Q1: Q5; Your answer Q2: $\sqrt{1^2 + 1^2} = 1.41$.
[5 empty] | RA18 | Your answer Q1: Q1; Your answer Q2: Length = 50\% of 16 = 8 time units. See MS Excel solution file, tab "RA18".
[5 empty] | RA18 | Your answer Q1: Q2; Your answer Q2: Length = 50\% of 6 = 3 time units.
[5 empty] | RA18 | Your answer Q1: Q3; Your answer Q2: The cut and paste method ignores the long tail and takes 50\% of the short durations, so it will probably underestimate the real duration.
[5 empty] | RA18 | Your answer Q1: Q4; Your answer Q2: A high value for the coefficient of variation means that standard deviation is likely to be high compared to the average durations. The cut and paste method ignores the standard deviation.
[5 empty] | RA18 | Your answer Q1: Q5; Your answer Q2: This activity has no risk and should therefore not be taken into consideration when buffering the critical chain.
[5 empty] | RA19 | Your answer Q1: Q1; Your answer Q2: $\sqrt{(6-4)^2+(10-6)^2+(2-1)^2+(2-1)^2+(6-4)^2} = 5.1$. See MS Excel solution file, tab "RA19".
[5 empty] | RA19 | Your answer Q1: Q2; Your answer Q2: $\sqrt{(5-3)^2+(5-3)^2} = 2.8$.
[5 empty] | RA19 | Your answer Q1: Q3; Your answer Q2: Long chains will overestimate the size of the buffers since the variability will be summed up. However, in reality, the variability will cancel out at some places in the chain.
[5 empty] | RA19 | Your answer Q1: Q4; Your answer Q2: If it is assumed that the length of the critical chain is equal to its expected duration, then it can be found on the normal distribution that adding two times sigma to the average is equal to the $97.5^{th}$ percentile, and the probability to exceed is then equal to 2.5\%.
[5 empty] | RA20 | Your answer Q1: Q1; Your answer Q2: This is the only arc that enters the critical chain.
[5 empty] | RA20 | Your answer Q1: Q2; Your answer Q2: A resource buffer should be added every time a new type of resource is used in the CC. In this scenario the CC changes resources twice, hence two resource buffers should be added: one for resource B and one for resource C. One could argue to add 3 resource buffers, i.e. also a resource buffer for resource A for activity 5.
[5 empty] | RA20 | Your answer Q1: Q3; Your answer Q2: The CNC is equal to the number of arcs over de number of nodes.
[5 empty] | RA20 | Your answer Q1: Q4; Your answer Q2: One could argue that some of the precedence relations are superfluous (arcs 2 - 5 and 2 - 6) resulting in a CNC = 3/4 but these precedence relation can not always be removed (e.g. if these precedences are different from the default FS = 0 type, removing these precedences might lead to a violation of some of the intended precedence relations).
[5 empty] | RA20 | Your answer Q1: Q5; Your answer Q2: The total standard deviation of the activities in the feeding chain is equal to $\sqrt(0.5^2+0.5^2+1.5^2+0.5^2)=1.73$, and hence, the size is equal to $1.73 * (1 + 5/4)=3.90$.
[5 empty] | RA20 | Your answer Q1: Q6; Your answer Q2: The total standard deviation of the activities in the critical chain is equal to $\sqrt(2.5^2+2.5^2+3.5^2)=4.97$, and hence, the size is equal to $4.97 * (1 + 2/3)=8.29$.
[5 empty] | RA21 | Your answer Q1: Q1; Your answer Q2: One project buffer and one feeding buffer should be used. Assuming a buffer is used for each resource, the total number of buffers is $2 * 3 = 6$.
[5 empty] | RA21 | Your answer Q1: Q2; Your answer Q2: The critical chain is equal to 1 - 2 - 3 - 5 - 6 - 7 with length 19, and hence, the available work content is equal to 2 (= availability of resource A) * 19 = 38. See MS Excel solution file, tab "RA21".
[5 empty] | RA21 | Your answer Q1: Q3; Your answer Q2: Activity 4 has a duration of 3 and uses 1 unit of resource C, so the work content used is 3 * 1 = 3.
[5 empty] | RA21 | Your answer Q1: Q4; Your answer Q2: The tightest resource is B so K = $\frac{15}{19}$. The size of the critical chain is then equal to $2.739 * (1 + K)$ (the standard deviation of the CC = $\sqrt{1^2+1^2+2^2+0.5^2+0.5^2+1^2}=2.739$). See MS Excel solution file, tab "RA21".
[5 empty] | RA21 | Your answer Q1: Q5; Your answer Q2: The tightest resource is C (only resource used by activity 4) (so K = $\frac{3}{6}$ = K. The size of the feeding chain is then equal to $1 * (1 + K)$ (the standard deviation of the FC = $\sqrt{1^2}=1$). See MS Excel solution file, tab "RA21".
[5 empty] | RA22 | Your answer Q1: Q1; Your answer Q2: Buffers can shift activities in time, resulting in new resource conflicts.
[5 empty] | RA22 | Your answer Q1: Q4; Your answer Q2: After inserting buffers, the longest chain (critical chain) can be shorter than another chain. There is currently no good solution to this problem, only pragmatic solutions, as discussed in article "RA23".
[5 empty] | RA23 | Your answer Q1: Q5; Your answer Q2: If feeding buffers are randomly split, it is likely that the second buffer is too small compared to the high variability of the activities entering that buffer.

## Summary PC
| Project control |  |  |  | Questions | Your answer
| Topic |  |  | Quiz? | Article ID | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7
1 | Dynamic scheduling | An introduction to project control |  | No | PC1 | - | - | - | - | - | - | -
2 | Earned Value Management | Earned Value Management: An overview |  | Yes | PC2 | b* | a | b* | b* | a | a | b*
3 |  | Earned Value Management: The EVM formulary |  | Yes | PC3 | a | a | a | b* | b | d* | -
4 |  | EVM Key metrics | Earned Value Management: The project baseline schedule’s planned value | Yes | PC4 | a | b* | b* | a | d* | c* | -
5 |  |  | Earned Value Management: The three key metrics | Yes | PC5 | b* | a | a | c* | a* | c* | -
6 |  |  | Measuring Time: Earned value or earned schedule? | Yes | PC6 | a | a | a | b* | a* | a* | -
7 |  | EVM Performance measurement | Earned Value Management: An overview of project performance scenarios | Yes | PC7 | a | a | a* | b | d* | c* | -
8 |  |  | Earned Value Management: Measuring a project’s performance | Yes | PC8 | a | a | b* | a* | a* | a* | b*
9 |  |  | Earned Value Management: Reliable time performance measurement | Yes | PC9 | a | c* | b | c* | a* | b* | -
10 |  | EVM Forecasting | Earned Value Management: Forecasting project outcome | Yes | PC10 | b | b* | a | b* | b | a* | -
11 |  |  | Earned Value Management: Forecasting time | Yes | PC11 | b* | a | a* | b* | d* | c* | -
12 |  |  | Earned Value Management: Forecasting cost | Yes | PC12 | b* | b* | b* | b* | b | b | -
13 |  |  | Predicting project performance: Evaluating the forecasting accuracy | Yes | PC13 | b* | a | a* | c* | a* | - | -
14 |  | Schedule adherence | Earned Value Management: Measuring schedule adherence | Yes | PC14 | b* | a | a | d* | a* | - | -
15 |  |  | Earned Value Management: Schedule adherence and the effective earned value | Yes | PC15 | a | a* | a* | b* | d | b* | -
16 |  |  | Earned Value Management: Identifying the lack of schedule adherence | Yes | PC16 | b* | a | b* | b* | c* | - | -
17 | Schedule control | Bottom-up project control: Setting action thresholds using schedule risk analysis |  | Yes | PC17 | a | b* | a | b* | a | b | -
18 |  | Top-down project control: Setting action thresholds using earned value management |  | Yes | PC18 | b* | b* | a | a* | a | d* | -
19 |  | Why project control works so well for some projects and fails so miserably for others |  | Yes | PC19 | a | b* | a* | b* | a | b* | a
20 |  | Schedule prediction: From a retained to an overridden logic |  | Yes | PC20 | b* | a* | a | b* | a | b* | -
21 |  | Updating the schedule: Setting actual and remaining cost values of activities in progress |  | Yes | PC21 | a | b* | a | a* | a | - | -
[5 empty] | Total number of questions: | 119
[5 empty] | Total number of comments: | 72
Comments:
[5 empty] | PC2 | Q1 | EVM is used both prior to the start (PV curve) and during progress (AC and EV).
[5 empty] | PC2 | Q3 | PV can also be called budgeted cost of work scheduled (BCWS).
[5 empty] | PC2 | Q4 | ES is expressed in time units.
[5 empty] | PC2 | Q7 | Similar to EV = BAC at the end of the project, ES = PD.
[5 empty] | PC3 | Q4 | The schedule adherence is expressed by the p-factor.
[5 empty] | PC3 | Q6 | SPI(t) = ES / AT.
[5 empty] | PC4 | Q2 | A project can have multiple critical paths.
[5 empty] | PC4 | Q3 | B; The planned duration is calculated by summing the durations of the activities on (one of) the critical path(s).
[5 empty] | PC4 | Q5 | All paths are critical except one (1-3-5-8).
[5 empty] | PC4 | Q6 | A change in the activity cost has no impact on the duration of the project nor on the critical path, but on the total cost (budget at completion) of the project.
[5 empty] | PC5 | Q1 | There is no information given on the expected delay of the project, thus the earned value can be situated both above or below the planned value.
[5 empty] | PC5 | Q4 | EV = Percentage completion * BAC.
[5 empty] | PC5 | Q5 | The actual cost lies above the earned value, so a cost overrun is to be expected. The earned value lies below the planned value, so a delay is to be expected.
[5 empty] | PC5 | Q6 | The actual finish time is given in figure 10.5. The actual estimated cost = cost incurred until evaluation point (30+60+30+30+20) + planned cost for remaining activities (20+20+20) = 230.
[5 empty] | PC6 | Q4 | When the project is finished, ES = PD.
[5 empty] | PC6 | Q5 | Linear interpolation is used when the EV at an evaluation point is not exactly equal to any of the recorded planned values. This is then used to calculate the ES.
[5 empty] | PC6 | Q6 | Both earned values will be projected on the same point on the PV-curve.
[5 empty] | PC7 | Q3 | The SV(t) metric does not have a quirky behaviour at the end of the project, while the SV metric does.
[5 empty] | PC7 | Q5 | AC > EV (cost overrun) and EV > PV (ahead of schedule).
[5 empty] | PC7 | Q6 | AC > EV (cost overrun) and EV < PV (late).
[5 empty] | PC8 | Q3 | SV is also expressed in monetary units (SV(t) is expressed in time units).
[5 empty] | PC8 | Q4 | The SPI in period 8 = 120 / 140 = 0.86 > 0.69 (SPI in period 7), so improved schedule performance.
[5 empty] | PC8 | Q5 | The CPI in period 8 = 120 / 200 = 0.60 > 0.53 (CPI in period 7), so improved cost performance.
[5 empty] | PC8 | Q6 | CV = 70 -120 = -50.
[5 empty] | PC8 | Q7 | SPI = EV / PV and CPI = EV / AC. Since the EV line lies below the PV line, which lies below the AC line, CPI < SPI throughout the entire project.
[5 empty] | PC9 | Q2 | Be careful since SV(t) = 0 means on time. Do not confuse SV(t) with SPI(t) (= 1 means on time).
[5 empty] | PC9 | Q4 | The projection of the EV at week 5 on the PV curve shows that this occurs somewhere between weeks 4 and 5 on the horizontal axis.
[5 empty] | PC9 | Q5 | At the end of the project, EV = PV and hence, SV = EV - PV = 0.
[5 empty] | PC9 | Q6 | Is SPI(t) = 1 at the project end, it means the project finishes on time. SPI is always equal to 1 at the end of the project.
[5 empty] | PC10 | Q2 | EAC(€) is a forecast to measure the expected deviation from the BAC, and can be equal to BAC, but also larger or smaller.
[5 empty] | PC10 | Q4 | If AC > PV > EV, the project is expected to exceed budget and finish late. In this case, both CPI and SPI/SPI(t) are smaller than 1.
[5 empty] | PC10 | Q6 | SCI = SPI * CPI.
[5 empty] | PC11 | Q1 | $TV=\frac{SV}{PV_{rate}}=\frac{SV*PD}{BAC}$ which is not equal to SV = EV - PV.
[5 empty] | PC11 | Q3 | Negative values are prohibited by the use of max(PD, AT) in the formula.
[5 empty] | PC11 | Q4 | The performance factor is equal to 1, SPI(t) or SPI(t) * CPI.
[5 empty] | PC11 | Q5 | None of them are always correct. In (a) CPI should be SPI, in (b) PD should be max(PD, AT), in (c) SCI should be SCI(t).
[5 empty] | PC11 | Q6 | (a) $EAC(t)_{PV1} = PD - TV = PD-\frac{SV*PD}{BAC} = PD*(1-\frac{SV}{BAC})$, (b) $AT+\frac{AT - ED}{SPI}=\frac{AT*SPI+AT-AT*SPI}{SPI}=\frac{AT}{SPI}$, (c) EV should be ES.
[5 empty] | PC12 | Q1 | The performance factor PF determines the future expected performance.
[5 empty] | PC12 | Q2 | SPI = EV / PV and SPI(t) = ES / AT.
[5 empty] | PC12 | Q3 | Both are dimensionless metrics, but the metrics used to calculated the indices, EV, AC and PV, are expressed in monetary units, while AT is expressed in time units.
[5 empty] | PC12 | Q4 | The $PV_{rate}$ is used for time predictions when the planned value method is applied.
[5 empty] | PC13 | Q1 | Interval estimates are used to incorporates uncertainty inherent to each project.
[5 empty] | PC13 | Q3 | Summing positive and negative values can result in a lower absolute value for MPE than MAPE.
[5 empty] | PC13 | Q4 | $MAPE=\frac{¦9-10¦+¦10-10¦+¦9-10¦}{3*10}=0.0667$, $MPE=\frac{(9-10)+(10-10)+(9-10)}{3*10}=-0,0667$.
[5 empty] | PC13 | Q5 | $MAPE=\frac{¦140-150¦+¦150-150¦+¦160-150¦}{3*150}=0,0444$, $MPE=\frac{(140-150)+(150-150)+(160-150)}{3*150}=0$.
[5 empty] | PC14 | Q1 | Higher values for the p-factor means better schedule adherence.
[5 empty] | PC14 | Q4 | p = (min(10,10) + min(25,15) + min(5,5) + min(30,40)) / (10 + 25 + 5 + 30) = 0.86. See MS Excel solution file, tab "PC14".
[5 empty] | PC14 | Q5 | Since ES does not change, the vertical ES line in figure 10.16 remains at the same place. As activity 4 is more expensive than activity 7, a smaller portion of the activity is performed under risk (i.e. the portion of the activity progress to the right of the ES line), so the p-factor increases. More specifically, the new p-factor is (10 + 30 + 5 + 2.8 + 0 + 40 + 0) / (10 + 30 + 5 + 2.8 + 1.4 + 40 + 0.7) = 0.977 instead of (10 + 30 + 5 + 0 + 0 + 40 + 0.7) / (10 + 30 + 5 + 2.8 + 1.4 + 40 + 0.7) = 0.953. See MS Excel solution file, tab "PC14".
[5 empty] | PC15 | Q2 | Plugging p = 1 into the formula results in EV(e) = EV.
[5 empty] | PC15 | Q3 | Since p has a maximum value of 1, EV(e) must be smaller than or equal to EV.
[5 empty] | PC15 | Q4 | R% represents the estimated portion of EV(r) that requires NO rework, so R% should be lowered when the risk of rework increases in a project.
[5 empty] | PC15 | Q6 | Only (a portion of) activity 7 lies to the right of the ES line.
[5 empty] | PC16 | Q1 | EV(e) is the sum of the risk-free earned value and a FRACTION of the risky earned value (i.e. the estimated portion R% that requires no rework).
[5 empty] | PC16 | Q3 | These activities can still show PV and EV accrue deviations which decrease the schedule adherence.
[5 empty] | PC16 | Q4 | It is possible that all activities show a uniform delay, meaning that no portion of the work performed lies to the right of the ES line. In this case, there is indeed a delay, but the delay is perfectly in accordance with the schedule, resulting in a p-factor of 1.
[5 empty] | PC16 | Q5 | The schedule adherence is not related to AC.
[5 empty] | PC17 | Q2 | Risk measures are defined on the activity level.
[5 empty] | PC17 | Q4 | A higher degree of attention might be required, but this does not necessarily result immediately in corrective actions.
[5 empty] | PC18 | Q1 | They provide information about the overall performance of the project.
[5 empty] | PC18 | Q2 | One can easily set a dynamic action threshold, and it is advised to do so since the attention (thresholds) should change along the project progress.
[5 empty] | PC18 | Q4 | More point will likely lie below the line, resulting in an increased intensity of control.
[5 empty] | PC18 | Q6 | Normally, the EVM top-down project control approach provides one single metric at the top of the WBS, while the bottom-up control approach provides several activities to monitor at the bottom of the WBS, and hence, answer (a) would be the best answer. But since the question ignores the number of times problems are detected, it is quite likely that the top-down approach warns for many problems, and then the control approach is very intensive. Therefore, the best possible answer is (d).
[5 empty] | PC19 | Q2 | If an action threshold is reached, the project manager will have to drill down to the activity level to identify the poor performing activities and take actions on them.
[5 empty] | PC19 | Q3 | When action thresholds are lowered, it means they shift to the right, and then more activities have sensitivity values (e.g. for the SSI) that exceed the threshold, leading to a more intensive control approach.
[5 empty] | PC19 | Q4 | When action thresholds are lowered, it means that the EVM metrics (e.g. the SPI(t)) will likely fall less below the threshold value, leading to a less intensive control approach. Note that this is only true when the thresholds lie below 1. A threshold above 1 (to detect opportunities instead of problems) will results in a more intensive control approach when the thresholds are lowered.
[5 empty] | PC19 | Q6 | It is known that EVM works better for serial networks, while SRA works better for parallel networks.
[5 empty] | PC20 | Q1 | An overridden logic violates precedence relations, but not always. Think e.g. of two activities without overlaps (no fast tracking). There is no reason to override the logic of the precedence relations.can always be activities for which the precedence relations are not violated when applying an overridden logic, e.g. when no fasttracking has occured.
[5 empty] | PC20 | Q2 | In a completely parallel network there are no precedence relations to be violated.
[5 empty] | PC20 | Q4 | It is exactly the opposite.
[5 empty] | PC20 | Q6 | 20 + 18 - 0.25 * 12 = 35. The last term (0.25 * 12) represents the reduction in project duration resulting from the 25% overlap which is allowed when the percentage overridden/retained is 75%.
[5 empty] | PC21 | Q2 | The fixed cost of an activity is fully incurred at the start of that activity.
[5 empty] | PC21 | Q4 | Since the fixed costs have been paid, only the remaining variable costs should be taken into account, and hence, PRC = 12 * € 75 + 18 * € 100 = € 2,700.